# Project Details
The RFP outlines a project for developing a hybrid Digital Twin (DT) framework for an Aero Gas Turbine Engine Health Usage Monitoring System, specifying tasks across phases from design to deployment and validation.
## Key Tasks Requested
- Develop physics-based thermodynamic models for major engine components and subsystems, augmented by data-driven models using test data from 50-60 engine tests (ground, simulated altitude, flight) to create 17 DT blocks.
- Integrate models into a real-time computational framework with virtual sensors, sensor validation/recovery, optimal sensor selection (type/ location via observability), non-dimensional performance parameters, fault seeding for alarms, and GUI with drag-and-drop, data visualization, warnings/ alarms, and storage/ retrieval.
- Handle large heterogeneous data (design, FEM/ CFD simulations, engine tests), perform data integrity checks, pre-processing, feature extraction, and ML training (70/ 30 train/ validation split).
- Procure/ supply hardware platform with real-time OS/ libraries, deploy framework, train models on-site with DRDO data (no external sharing), and conduct anomaly detection/ isolation via error comparison against engine-to-engine tolerances.
- Prepare documentation (SRD, SDD, DDD, CDD, ATP, user manual), execute ToT, share IPR per terms, and validate models (≤5% error for DT blocks, ≤10% for virtual sensors using MAE, R², max error).
## Nature of Work
The work involves multidisciplinary engineering: aerothermodynamics for physics models, ML/ AI for data-driven augmentation (e.g., regression, anomaly detection), software integration for real-time simulation, and hardware deployment. It requires expertise in tools (open-source/ commercial/ in-house like NPSS/ GasTurb), data pipelines for large datasets, and domain knowledge in engine failure modes under flight conditions. Critical technologies include AI-augmented thermodynamics and virtual sensors, with on-site collaboration at DRDO premises for data security.
## Effort and Timeline
Effort spans high-fidelity modeling (initial physics + data fusion), integration/testing (offline/ online), and production (hardware/ software supply), demanding a team skilled in simulation, data science, and systems engineering over 36 months. Milestones include PDR (6 months, 20% payment), Detailed Design (12 months, 40%), Prototype (18 months, 60%), Production (30 months, 80%), and Completion/ToT (36 months, 100%).
## Project Plan Phases
Phase	Key Activities	Milestones/Deliverables	Timeline (Months)
PDR	Requirements finalization, tech survey, PDD approval	Approved PDD/SRD	6
Detailed Design	17 DT block designs, data pre-processing, BOM	Approved SDD/DDD	12
Prototype	Integrated model realization, validation with test data	Approved CDD, prototype reports	18
Production	Hardware procurement, on-site training/deployment, ATP	Verified hardware/software, acceptance reports	30
Completion	Documentation, ToT, IPR sharing	Project success report, full framework supply	36

## Expected Outcomes
Outcomes include a deployable hybrid DT framework mimicking engine behavior for diagnostics/prognostics, with real-time GUI, virtual sensors, and anomaly alarms; validated hardware/software platform; comprehensive docs; and metrics-proven fidelity (e.g., <5% model error) for lifecycle monitoring. Success enables DRDO-independent use, with ATP committee evaluation of FoM, indigenous content, and recommendations.
# Project Plan
The project plan for developing a hybrid Digital Twin (DT) framework for Aero Gas Turbine Engine Health Usage Monitoring System follows the 36-month timeline and milestones outlined in the PDD, with detailed activities, resources, and estimates derived from project requirements and industry benchmarks for similar aerospace DT initiatives.appinventiv+1​
## Timeline and Milestones
The overall timeline spans 36 months, divided into five phases with gated reviews and payments tied to milestones (20% at MS1, cumulative 40% at MS2, etc.).
Phase	Duration (Months from Start)	Key Milestone	Deliverables
Preliminary Design Review (PDR)	0-6	MS1: Approved PDD/SRD	System Requirement Document (SRD), tech survey report, DT architecture
Detailed Design	6-12	MS2: Approved SDD/DDD	Detailed designs for 17 DT blocks, data pre-processing plan, tentative BOM
Prototype Realization	12-18	MS3: Approved CDD	Integrated prototype, offline/online validation reports, <5% error on DT blocks
Production and Supply	18-30	MS4: Acceptance Test Report	Hardware/software supply, on-site model training, ATP execution
Documentation and ToT	30-36	MS5: Project Completion	Full docs, ToT execution, IPR sharing, verified framework (<10% virtual sensor error)

## Resources Needed
A multidisciplinary team of 15-20 personnel is required, scaling from 8 in early phases to peak 20 during integration, based on complexity of aero-thermodynamics, ML, and real-time systems in similar projects. Computational resources include high-performance servers for training (e.g., GPU clusters) and real-time hardware (RTOS like VxWorks).reddit+1
- Human Resources:
  - 4-6 Aerospace/Thermodynamics Engineers (physics-based modeling with NPSS/GasTurb).
  - 4-5 Data Scientists/ML Engineers (data-driven fusion, virtual sensors, anomaly detection).
  - 3-4 Software Engineers (GUI, real-time integration, Python/C++).
  - 2 Systems Engineers (hardware procurement, observability analysis).
  - 2 Project Managers/Quality Leads (reviews, ATP).

- Hardware/Software:
  - Development: GPU workstations (e.g., NVIDIA A100), simulation tools (NPSS, ANSYS, open-source like PyTorch).
  - Deployment: Real-time servers (e.g., industrial PCs with RTOS), ~400 test runs data access at DRDO site.
  - Data: ~50-60 engine tests (ground/altitude/flight), FEM/CFD datasets.swri​
## Estimated Expenses
Total project cost estimated at $5-10M (scaled from oil/gas DT benchmarks of $0.5-4M and aerospace complexity like HyTEC's $80-100M shared funding), with 40-50% manpower, 20-30% hardware/tools, 20% testing/data, 10% overhead; payments milestone-linked at 20% increments.appinventiv+1​
Category	Estimated Cost (% of Total)	Breakdown
Manpower	45% ($2.25-4.5M)	Salaries (₹20-50L/year/engineer), 36 months reddit​
Hardware	25% ($1.25-2.5M)	RTOS servers, GPUs, sensors (~$500K+ deployment)
Software/Tools	15% ($0.75-1.5M)	Licenses (NPSS/GasTurb), cloud compute swri​
Testing/Travel	10% ($0.5-1M)	On-site DRDO validation, data handling
Overhead/Misc	5% ($0.25-0.5M)	Documentation, ToT, contingencies

## Information Needed
Access to proprietary data and specs is critical, provided progressively at DRDO premises to ensure security.
- Engine-specific details: Geometry, performance maps, 17 DT block definitions (e.g., compressor, turbine), failure modes.
- Test data: ~400 runs (70/30 train/validation split), PLA/flight conditions (altitude, Mach, inlet T/P).
- Validation criteria: Exact FoM, error bands (≤5% DT, ≤10% sensors), engine-to-engine tolerances, ATP template.
- Infrastructure: DRDO site for on-site training/deployment, sensor data formats.
## Key Activities
Activities follow a gated process with DRDO reviews, emphasizing hybrid model fidelity (physics + data-driven via regression/ML).
- PDR (0-6M): Requirements finalization, literature survey on AI-thermodynamics/virtual sensors, architecture design.
- Detailed Design (6-12M): Develop 17 physics-based DT blocks, data pre-processing/feature selection, hybrid fusion design, BOM finalization.
- Prototype (12-18M): Model integration, offline/online testing, clustering fused data, subsystem validation with synthesized data.
- Production (18-30M): Hardware procurement/integration, on-site ML training (no data export), GUI development, fault seeding/anomaly detection.
- Completion (30-36M): ATP execution by committee (FoM eval, indigenous content), docs/ToT, IPR handover.
## Tangible and Measurable Outcomes
Outcomes are quantifiable via PDD metrics, ensuring deployable DT for diagnostics/prognostics.
- Hybrid DT framework (17 blocks) with ≤5% error (MAE, R², max error) vs. physical engine.
- Virtual sensors (≤10% error), optimal sensor sets/locations via observability.
- Real-time GUI (drag-drop, alarms, visualizations), hardware platform, anomaly isolation logic.
- Docs (SRS/SDD/DDD/CDD/ATP/User Manual), trained models on 400+ tests, project success report.
- Committee-validated FoM (e.g., prediction accuracy >95%), indigenous content analysis.
Risks include data access delays (mitigate via early SRD) and model convergence (address with iterative 70/30 validation); success enables lifecycle engine monitoring.
1. https://appinventiv.com/blog/digital-twin-in-oil-and-gas/
2. http://goldfinger.utias.utoronto.ca/IWACC8/UTIAS_IWACC8_TonyNerone.pdf
3. https://www.reddit.com/r/AerospaceEngineering/comments/1dp6pd9/modeling_and_simulation_engineers/
4. https://www.swri.org/markets/electronics-automation/software/aerospace-software/numerical-propulsion-system-simulation-npss
5. https://www.visioneerit.com/blog/digital-twin-technology-the-260-billion-revolution-transforming-industries
6. https://www.sciencedirect.com/science/article/abs/pii/S1359431124006227
7. https://www.gevernova.com/software/innovation/digital-twin-technology
8. https://www.anylogic.com/resources/case-studies/atom-digital-twin-of-siemens-gas-turbine-fleet-operations/
9. https://webthesis.biblio.polito.it/25652/1/tesi.pdf
10. https://www.sciencedirect.com/science/article/abs/pii/S0967066124001746
11. https://www.cranfield.ac.uk/courses/short/aerospace/aero-digital-twin-technologies-for-gas-turbine-engines
12. https://www.arxiv.org/pdf/2506.19503.pdf
13. https://dataintelo.com/report/digital-twin-gas-turbine-market
14. https://ntrs.nasa.gov/api/citations/20230012237/downloads/TM-20230012237_Final.pdf
15. https://www.linkedin.com/advice/0/youre-facing-budget-constraints-aerospace-pfufe
16. https://www.theseus.fi/bitstream/handle/10024/502736/Master's%20Thesis-Hamid%20Asgari.pdf?sequence=2&isAllowed=y
17. https://www.cal-tek.eu/proceedings/i3m/2023/sesde/003/pdf.pdf
18. https://www.theforage.com/simulations/ge-aerospace/human-resources-8hl7
19. https://www.capgemini.com/us-en/wp-content/uploads/sites/30/2022/05/six-budget-considerations-for-digital-aviation-transformation-final.pdf
20. https://www.cambridge.org/core/product/0415A99D66D539ACBB9173AE2A1CD7A6/core-reader

# Key restrictions, constraints, enablers, and strengtheners
Key restrictions and constraints in the project stem from data security protocols and validation rigor, while enablers include phased funding and DRDO collaboration; strengtheners leverage hybrid modeling and standardized milestones.
## Restrictions
- Strict data security: Engine test data (~400 runs) cannot be shared outside DRDO premises; all model training, modifications, and evaluations must occur on-site with DRDO oversight.
- No data export: Raw/sensitive engine run data (ground, altitude, flight tests) restricted to user premises, limiting off-site development and requiring physical presence for ~70/30 train/validation cycles.
- No exemptions: Zero waivers for startups or MSMEs on procurement, compliance, or deliverables.
## Constraints
- Tight fidelity metrics: DT blocks must achieve ≤5% error (MAE, R², max error) vs. physical engine; virtual sensors ≤10% error; deviations trigger ATP committee rejection.
- Fixed timeline and scope: 36-month schedule with gated milestones (PDR at 6M, completion at 36M); scope limited to one specified aero gas turbine engine and 17 DT blocks.
- Resource dependencies: Reliance on DRDO-provided data/formats, mutual-agreed hardware platforms, and committee approvals for FoM, indigenous content, and ATP.
- Payment linkage: Milestone-based disbursements (20% increments), halting progress if reviews fail.
## Enablers
- Phased funding: Cumulative payments (20% at MS1/PDR, up to 100% at MS5) aligned with deliverables, enabling resource scaling.
- Collaborative validation: Joint on-site evaluations with DRDO team, including synthesized data access and minor train/validation split variations per review committee.
- Tool flexibility: Use of open-source, commercial (e.g., NPSS), or in-house tools for physics/data-driven models; real-time OS libraries provided in scope.
- Structured process: Defined ATP document (finalized at PDR), anomaly detection framework (error banding vs. engine tolerances), and ToT/IPR sharing per TDF Scheme SOP.
## Strengtheners
Category	Details	Impact
Hybrid Approach	Physics-based thermodynamics augmented by data-driven ML (regression, feature selection) for 17 blocks, virtual sensors, and fault seeding	Enhances fidelity, adaptability to failure modes/flight conditions; supports diagnostics/prognostics.
Comprehensive Framework	Includes GUI (drag-drop, alarms, visualizations), sensor optimization (observability-based), data integrity checks, and large heterogeneous data handling (FEM/CFD/tests)	Enables real-time monitoring, decision-making across engine lifecycle.
Rigorous Testing	70/30 split on 400+ tests; anomaly isolation via PLA/flight input comparisons; FoM evaluation by formal committee	Ensures deployable reliability, quantifies success (e.g., >95% accuracy targets).
Indigenous Focus	ATP analysis of local content; scalable to user quantities per DPR/PDD	Boosts strategic value, potential for broader DRDO adoption.

# Work Breakdown Structure (WBS)
Below is a milestone-wise work breakdown structure (WBS) aligned exactly with the PDD milestones MS‑1 to MS‑5, expanded into concrete tasks and sub-tasks for execution and tracking.​

## MS‑1 (T0–4 Months) – Preliminary Design Review
Objective: Freeze requirements, architecture, and preliminary design baseline.
### 1.1 Project Initiation & Governance
- Define project organization (roles, RACI, review committees) and communication plan.​
- Establish configuration management, document control, and toolchain (repo, issue tracker).
### 1.2 Requirement Elicitation & Clarification
- Conduct user interaction sessions with the DRDO lab to understand engine, Hums requirements, and operational constraints.​
- Capture functional and non-functional requirements (real-time, accuracy ≤5%/≤10%, security, data residency).
### 1.3 System Requirements Document (SRD)
- Draft SRD covering: system scope, interfaces, performance metrics, test and acceptance criteria.​
- Iterate with DRDO for comments; baseline SRD as an approved configuration item.
### 1.4 Technology Survey & Critical Technology Identification
- Perform literature survey on:
  - Physics-based gas turbine thermodynamic modeling.
  - AI-augmented models and virtual sensors for aero engines.
  - Hybrid DT architectures and anomaly detection methods.​
- Identify critical technologies:
  - AI-augmented thermodynamic model.
  - Virtual sensors.
  - Hybrid model fusion framework.​
### 1.5 High-Level DT Framework & Architecture
- Define 17 DT building blocks using commercial/off-the-shelf, open-source, and in-house tools as permitted.​
- Prepare logical and physical architecture diagrams (data flows, interfaces, real-time paths, storage).
### 1.6 Preliminary Design Document (PDD) Finalization
- Consolidate SRD, architecture, critical tech list, and preliminary design assumptions into PDD.​
- Conduct internal pre-PDR review → address findings → present to DRDO PDR committee.
- Achieve formal PDD approval as the MS‑1 deliverable (20% payment).​

## MS‑2 (T0–12 Months) – Detailed Design & Engineering Prototype Definition
Objective: Complete detailed design of all DT blocks and integrated system, with engineering prototype definition.
### 2.1 Feasibility & Modeling Strategy per Component
- For each of the 17 DT blocks, decide physics-based, data-driven, or hybrid modeling strategy based on feasibility study.​
- Document rationale (data availability, modeling complexity, real-time constraints).
### 2.2 Detailed Design of DT Blocks (Component-Level)
- Develop detailed thermodynamic models for major components (compressor, combustor, turbine, nozzle, etc.).​
- Specify equations, maps, operating envelopes, and failure-mode representations.
- Design data-driven models (regressors/NNs) for blocks selected for ML augmentation.
### 2.3 Data Strategy & Pre-processing Design
- Plan collection and pre-processing of test data from 50–60 engine tests (ground, simulated altitude, flight).​
- Define feature selection, normalization, outlier handling, train/validation split (70/30), and storage schemas.
### 2.4 Integrated System Design (17 DT Blocks)
- Define integration of component DT blocks into full-engine DT model: interfaces, variable naming, units, timing.​
- Design architecture for sensor management, virtual sensors, anomaly detection, and Hums outputs.
### 2.5 Hardware & Platform Definition
- Finalize tentative Bill of Material (BoM) for:
  - Real-time computational platform.
  - Storage and networking.
  - Any specific DAQ/hardware as required.​
- Define OS/RTOS, libraries, and middleware.
### 2.6 System Design Document (SDD) & Detailed Design Document (DDD)
- Produce SDD (system-level) and DDD (component-level 17 DT blocks) as per PDD template.​
- Internal design reviews → DRDO design review for SDD/DDD approval, including engineering prototype definition (realization concept).
- MS‑2 achievement: Approved SDD + DDD + engineering prototype definition (cumulative 40% payment).​

## MS‑3 (T0–18 Months) – Prototype Development & Critical Design Review
Objective: Realize integrated DT prototype, perform offline/online validation, and secure CDD approval.
### 3.1 Prototype Implementation of DT Blocks
- Implement physics-based models for each component as per DDD.​
- Implement data-driven models (regression/ML) and hybrid fusion logic (per block).
### 3.2 Data Handling & Training
- Ingest and pre-process 50–60 engine tests; implement feature selection pipeline.​
- Train models using ~70% of ~400 runs for calibration and ~30% for validation (with committee-approved variations).​
- Store trained models and calibration parameters.
### 3.3 Integrated DT Prototype Assembly
- Integrate 17 DT blocks into a working engineering prototype model with:
  - Consistent I/O interfaces.
  - Coherent scheduling/timing for real-time simulation.
  - Basic GUI or console for internal testing.​
### 3.4 Performance Regime Clustering & Algorithm Tuning
- Cluster fused data into different performance regimes (e.g., idle, climb, cruise).​
- Develop and tune algorithms for regime-specific predictions and transitions.
### 3.5 Prototype Testing & Validation (Offline/Online)
- Offline: Run DT prototype against historical/synthesized test data, compute MAE, R², max error for each block.​
- Online (simulation mode): Test real-time execution behavior in an integrated environment (non-final platform is acceptable).
- Verify prototype DT performance at subsystem and integrated levels against engine test/synthesized data.​
### 3.6 Quality Assurance & Process Documentation
- Prepare process documents, quality assurance plan, and test reports for prototype verification.​
- Document deviations from targets, root cause analysis, and improvement actions.
### 3.7 Critical Design Document (CDD) & Critical Design Review (CDR)
- Compile CDD capturing final design choices after prototype lessons.​
- Conduct CDR with DRDO; demonstrate:
  - Prototype performance (offline/online).
  - Compliance with fidelity targets trend toward ≤5%/≤10% error.
- MS‑3 achievement: Source code & framework (initial version), test reports, QA plan, approved CDD (cumulative 60% payment).​

## MS‑4 (T0–30 Months) – Production & Supply, ATP Execution
Objective: Move from prototype to production-grade DT system, deploy hardware/software, and execute ATP.
### 4.1 Production-Grade Hardware Procurement & Setup
- Procure real-time supported hardware computational platform as per finalized BoM.​
- Install RTOS, drivers, and all necessary libraries; validate environment readiness.
### 4.2 Production Software Hardening
- Refine DT codebase into production version:
  - Performance optimization for real-time execution.
  - Exception handling, logging, fault tolerance.​
- Harden GUI with:
  - Drag-and-drop configuration.
  - Data presentation pane with alarms/warnings.
  - Pictorial engine and component views.​
### 4.3 Integration of Hardware & Software
- Integrate DT framework, GUI, and data management stack on production hardware.​
- Validate end-to-end pipeline from input (PLA, flight conditions) to Hums outputs, alarms, and storage.
### 4.4 Acceptance Test Procedure & Execution (ATP)
- Prepare detailed ATP document (based on Table‑1 building blocks and Section 4 of PDD).​
- Conduct ATP in DRDO environment:
  - Functional tests for all DT blocks.
  - Performance tests against accuracy criteria (≤5% DT blocks, ≤10% virtual sensors).
  - Real-time execution tests.
  - Sensor validation and recovery tests, optimal sensor set verification.
  - Anomaly detection tests with fault seeding.​
### 4.5 On-Site Model Training & Validation with DRDO Data
- Perform software development and tuning at user premises:
  - Data pre-processing, feature extraction, ML model re-training as needed.
  - Use ground, simulated altitude, and flight tests to finalize models.​
- No engine run data leaves DRDO premises; all modifications done in-house with DRDO participation.​
### 4.6 Acceptance Reports
- Prepare:
  - Acceptance test report.
  - Verification and validation report as per Para‑4 of PDD.​
- Facilitate user acceptance of supplied items (hardware + real-time DT model).​
- MS‑4 achievement: Verified & validated DT + GUI source code, hardware/software acceptance, ATP report, user manual draft (cumulative 80% payment).​

## MS‑5 (T0–36 Months) – Documentation, ToT, Project Closure
Objective: Complete documentation, execute ToT, finalize IPR, and close the project.
### 5.1 Final Documentation Set
- Complete project documentation including:
  - Synthesized framework description of aero gas turbine DT (physics + data-based models).
  - Hardware platform, OS, and libraries description.​
  - Full design & test documentation (SRD, SDD, DDD, CDD, ATP, V&V).
  - User manual, admin manual, troubleshooting guide.​
### 5.2 Production & Delivery of Final Deployable Units
- Deliver final integrated DT model (software + hardware) in required quantities as per DPR/PDD.​
- Verify final builds against ATP baselines and configuration records.
### 5.3 Transfer of Technology (ToT)
- Execute ToT as per TDF Scheme SOP:
  - Conduct training sessions for DRDO personnel on operation, tuning, and maintenance.
  - Hand over source code, build scripts, and configuration management procedures.
  - Demonstrate update flow for future engine variants.​
### 5.4 IPR Sharing & Legal Closure
- Implement IPR sharing as per Project Definition Document & RFP terms.​
- Finalize licensing documentation and rights allocation between DRDO and industry partner.
### 5.5 Project Success & Completion Reports
- Prepare:
  - Project success report (technical achievements, FoM, indigenous content).
  - Project completion report (scope, schedule, cost adherence, risk outcomes).​
- Support DRDO committee in final evaluation and recommendation for way ahead.​
- MS‑5 achievement: One complete DT framework set, hardware platform, full documentation, ToT executed, IPR shared (cumulative 100% payment).​
## WBS Gantt
WBS ID	Task Name	Start Week	End Week	Duration (Weeks)	Lead Role	Supporting Roles	Effort (PM)	Dependency
1.1	Project Initiation & Governance	1	4	4	Project Manager	Program Coordinator	2	-
1.2	Requirement Elicitation & Clarification	5	10	6	Systems Engineer	PM DRDO Liaison	4	1.1
1.3	System Requirements Document (SRD)	11	18	8	Systems Engineer	PM QA Lead	5	1.2
1.4	Technology Survey & Critical Tech ID	6	17	12	Lead ML/AI Scientist	Lead Thermo Eng Academics	8	1.1
1.5	High-Level DT Framework & Architecture	15	22	8	Software Architect	Systems Eng Lead Roles	6	1.4
1.6	PDD Finalization & PDR Approval	19	26	8	Project Manager	Systems Eng All Leads	4	1.3 1.5
2.1	Feasibility & Modeling Strategy	27	32	6	Lead Thermo Eng	Lead ML Sci Systems Eng	8	1.6
2.2	Detailed Design of 17 DT Blocks	33	48	16	Lead Thermo Eng	Lead ML Sci Data Eng	20	2.1
2.3	Data Strategy & Pre-processing Design	27	38	12	Data Engineer	Lead ML Sci QA Lead	10	1.6
2.4	Integrated System Design (17 DT Blocks)	39	48	10	Software Architect	Systems Eng Lead Thermo	12	2.2
2.5	Hardware & Platform Definition	35	42	8	Systems Engineer	Software Arch QA Lead	6	2.1
2.6	SDD/DDD Finalization & Design Review	45	52	8	Systems Engineer	PM All Technical Leads	6	2.2 2.4 2.5
3.1	Prototype Implementation of DT Blocks	53	66	14	Lead Thermo Eng	Lead ML Sci Soft Arch JE	24	2.6
3.2	Data Handling Training & Validation	53	68	16	Data Engineer	Lead ML Sci Lead Thermo	18	2.3
3.3	Integrated DT Prototype Assembly	63	72	10	Software Architect	Lead Thermo Eng Soft Eng	14	3.1
3.4	Performance Regime Clustering & Tuning	65	72	8	Lead ML/AI Scientist	Data Engineer Lead Thermo	10	3.2
3.5	Prototype Testing & Validation	67	76	10	QA Lead	Lead Thermo Eng QA Team	12	3.3 3.4
3.6	QA & Process Documentation	70	75	6	QA Lead	PM Technical Writers	8	3.5
3.7	CDD & Critical Design Review (CDR)	73	78	6	Systems Engineer	PM All Leads	6	3.6
4.1	Hardware Procurement & Setup	79	90	12	Systems Engineer	Soft Arch Admin Vendors	8	3.7
4.2	Production Software Hardening	85	100	16	Software Architect	GUI Dev Soft Eng QA	18	3.7
4.3	Hardware & Software Integration	99	110	12	Software Architect	Systems Eng Soft Team	14	4.1 4.2
4.4	ATP Procedure & Execution	109	124	16	QA Lead	PM All Teams DRDO	16	4.3
4.5	On-Site Model Training & Validation	95	114	20	Lead ML/AI Scientist	Data Eng Lead Thermo JE	22	4.2
4.6	Acceptance Reports & Final Sign-off	125	130	6	QA Lead	PM Systems Eng	4	4.4 4.5
5.1	Final Documentation Set	131	142	12	Project Manager	Tech Writers All Leads	8	4.6
5.2	Production & Delivery of Final Units	131	140	10	Software Architect	Systems Eng QA Admin	10	4.6
5.3	Transfer of Technology (ToT)	141	150	10	Lead Thermo Eng	Lead ML Sci All Leads	12	5.1
5.4	IPR Sharing & Legal Closure	145	150	6	Project Manager	Legal Advisor	3	5.1
5.5	Project Success & Completion Reports	150	156	7	Project Manager	Systems Eng QA Lead	5	5.3 5.4

## Team Effort
Role	Count	FTE	Monthly Rate (₹)	Annual Cost (₹)	36-Month Cost (₹)	Project Span
Project Manager	1	1	₹350,000.00	₹4,200,000.00	₹126,000,000.00	36 months (full-time)
Lead Thermodynamics Engineer	1	1	₹400,000.00	₹4,800,000.00	₹144,000,000.00	36 months (full-time)
Lead ML/AI Scientist	1	1	₹450,000.00	₹5,400,000.00	₹162,000,000.00	36 months (full-time)
Software Architect	1	0.8	₹350,000.00	₹3,360,000.00	₹100,800,000.00	30 months (80% after M24)
Data Engineer	1	1	₹300,000.00	₹3,600,000.00	₹108,000,000.00	36 months (full-time)
GUI/UX Developer	1	0.6	₹250,000.00	₹1,500,000.00	₹45,000,000.00	18 months (from M12)
Quality Assurance Lead	1	1	₹280,000.00	₹3,360,000.00	₹100,800,000.00	36 months (full-time)
Systems Engineer	1	0.5	₹280,000.00	₹1,680,000.00	₹50,400,000.00	12 months (part-time M0-M12)
Junior Thermodynamics Engineer	2	1	₹150,000.00	₹3,600,000.00	₹108,000,000.00	24 months (M6-M30)
ML Engineer / Research Associate	2	1	₹180,000.00	₹4,320,000.00	₹129,600,000.00	30 months (M0-M30)
Software Engineer / Developer	3	1	₹180,000.00	₹6,480,000.00	₹194,400,000.00	24 months (M12-M36)
Data Scientist / Analyst	1	1	₹200,000.00	₹2,400,000.00	₹72,000,000.00	18 months (M6-M24)
QA Engineer / Test Specialist	2	0.8	₹120,000.00	₹2,304,000.00	₹69,120,000.00	12 months (M18-M30)
Technical Writer	2	0.4	₹100,000.00	₹960,000.00	₹28,800,000.00	12 months (M24-M36)
Program Coordinator	1	0.5	₹80,000.00	₹480,000.00	₹14,400,000.00	36 months (part-time)
TOTAL TEAM	20	14.0 avg	-	₹58,000,000.00	₹450,000,000.00	-