## Overview
Parameter	Value
Project Name	Hybrid Digital Twin for Aero Gas Turbine Engine HUMS
Project Duration	36 months (156 weeks, 1092 days)
Project Start Date	Month 0, Week 1 (Day 1)
Project End Date	Month 36, Week 156 (Day 1,092)
Total Phases	5 milestones (MS-1 to MS-5)
Total Budget	₹15.30 Cr (approx ₹15.00 Cr)
Total Effort	305 Person-Months
Average Team Size	14 FTE

## Milestones
Milestone	Phase	Start Week	End Week	Duration	Payment Gate	Cumulative %
MS-1	PDR	1	26	6 months	20% (₹3.00 Cr)	20%
MS-2	Detailed Design	27	52	6 months	20% (₹3.00 Cr)	40%
MS-3	Prototype & CDR	53	78	6 months	20% (₹3.00 Cr)	60%
MS-4	Production & ATP	79	130	12 months	20% (₹3.00 Cr)	80%
MS-5	Completion & ToT	131	156	6 months	20% (₹3.00 Cr)	100%

## WBS
WBS ID	Task Name	Start Week	End Week	Duration (Weeks)	Lead Role	Supporting Roles	Effort (PM)	Dependency	4	8	12	16	20	24	28	32	36	40	44	48	52	56	60	64	68	72	76	80	84	88	92	96	100	104	108	112	116	120	124	128	132	136	140	144	148	152	156	160					Wk 1	Wk 2	Wk 3	Wk 4	Wk 5	Wk 6	Wk 7	Wk 8	Wk 9	Wk 10	Wk 11	Wk 12	Wk 13
1.1	Project Initiation & Governance	1	4	4	Project Manager	Program Coordinator	2	-	X
1.2	Requirement Elicitation & Clarification	5	10	6	Systems Engineer	PM DRDO Liaison	4	1.1		X
1.3	System Requirements Document (SRD)	11	18	8	Systems Engineer	PM QA Lead	5	1.2			X	X
1.4	Technology Survey & Critical Tech ID	6	17	12	Lead ML/AI Scientist	Lead Thermo Eng Academics	8	1.1		X	X	X
1.5	High-Level DT Framework & Architecture	15	22	8	Software Architect	Systems Eng Lead Roles	6	1.4				X	X
1.6	PDD Finalization & PDR Approval	19	26	8	Project Manager	Systems Eng All Leads	4	1.3 1.5					X	X
2.1	Feasibility & Modeling Strategy	27	32	6	Lead Thermo Eng	Lead ML Sci Systems Eng	8	1.6					X	X
2.2	Detailed Design of 17 DT Blocks	33	48	16	Lead Thermo Eng	Lead ML Sci Data Eng	20	2.1					X	X	X	X
2.3	Data Strategy & Pre-processing Design	27	38	12	Data Engineer	Lead ML Sci QA Lead	10	1.6					X	X	X
2.4	Integrated System Design (17 DT Blocks)	39	48	10	Software Architect	Systems Eng Lead Thermo	12	2.2					X	X	X
2.5	Hardware & Platform Definition	35	42	8	Systems Engineer	Software Arch QA Lead	6	2.1					X	X
2.6	SDD/DDD Finalization & Design Review	45	52	8	Systems Engineer	PM All Technical Leads	6	2.2 2.4 2.5					X	X
3.1	Prototype Implementation of DT Blocks	53	66	14	Lead Thermo Eng	Lead ML Sci Soft Arch JE	24	2.6					X	X	X
3.2	Data Handling Training & Validation	53	68	16	Data Engineer	Lead ML Sci Lead Thermo	18	2.3					X	X	X	X
3.3	Integrated DT Prototype Assembly	63	72	10	Software Architect	Lead Thermo Eng Soft Eng	14	3.1					X	X	X
3.4	Performance Regime Clustering & Tuning	65	72	8	Lead ML/AI Scientist	Data Engineer Lead Thermo	10	3.2					X	X
3.5	Prototype Testing & Validation	67	76	10	QA Lead	Lead Thermo Eng QA Team	12	3.3 3.4					X	X	X
3.6	QA & Process Documentation	70	75	6	QA Lead	PM Technical Writers	8	3.5					X
3.7	CDD & Critical Design Review (CDR)	73	78	6	Systems Engineer	PM All Leads	6	3.6					X
4.1	Hardware Procurement & Setup	79	90	12	Systems Engineer	Soft Arch Admin Vendors	8	3.7					X	X	X
4.2	Production Software Hardening	85	100	16	Software Architect	GUI Dev Soft Eng QA	18	3.7					X	X	X	X
4.3	Hardware & Software Integration	99	110	12	Software Architect	Systems Eng Soft Team	14	4.1 4.2					X	X	X
4.4	ATP Procedure & Execution	109	124	16	QA Lead	PM All Teams DRDO	16	4.3					X	X	X	X
4.5	On-Site Model Training & Validation	95	114	20	Lead ML/AI Scientist	Data Eng Lead Thermo JE	22	4.2					X	X	X	X	X
4.6	Acceptance Reports & Final Sign-off	125	130	6	QA Lead	PM Systems Eng	4	4.4 4.5					X
5.1	Final Documentation Set	131	142	12	Project Manager	Tech Writers All Leads	8	4.6					X	X	X
5.2	Production & Delivery of Final Units	131	140	10	Software Architect	Systems Eng QA Admin	10	4.6					X	X	X
5.3	Transfer of Technology (ToT)	141	150	10	Lead Thermo Eng	Lead ML Sci All Leads	12	5.1					X	X
5.4	IPR Sharing & Legal Closure	145	150	6	Project Manager	Legal Advisor	3	5.1					X
5.5	Project Success & Completion Reports	150	156	7	Project Manager	Systems Eng QA Lead	5	5.3 5.4					X	X

## Resource_Team
Role	Count	FTE	Monthly Rate (₹)	Annual Cost (₹)	36-Month Cost (₹)	Project Span
Project Manager	1	1	₹350,000.00	₹4,200,000.00	₹126,000,000.00	36 months (full-time)
Lead Thermodynamics Engineer	1	1	₹400,000.00	₹4,800,000.00	₹144,000,000.00	36 months (full-time)
Lead ML/AI Scientist	1	1	₹450,000.00	₹5,400,000.00	₹162,000,000.00	36 months (full-time)
Software Architect	1	0.8	₹350,000.00	₹3,360,000.00	₹100,800,000.00	30 months (80% after M24)
Data Engineer	1	1	₹300,000.00	₹3,600,000.00	₹108,000,000.00	36 months (full-time)
GUI/UX Developer	1	0.6	₹250,000.00	₹1,500,000.00	₹45,000,000.00	18 months (from M12)
Quality Assurance Lead	1	1	₹280,000.00	₹3,360,000.00	₹100,800,000.00	36 months (full-time)
Systems Engineer	1	0.5	₹280,000.00	₹1,680,000.00	₹50,400,000.00	12 months (part-time M0-M12)
Junior Thermodynamics Engineer	2	1	₹150,000.00	₹3,600,000.00	₹108,000,000.00	24 months (M6-M30)
ML Engineer / Research Associate	2	1	₹180,000.00	₹4,320,000.00	₹129,600,000.00	30 months (M0-M30)
Software Engineer / Developer	3	1	₹180,000.00	₹6,480,000.00	₹194,400,000.00	24 months (M12-M36)
Data Scientist / Analyst	1	1	₹200,000.00	₹2,400,000.00	₹72,000,000.00	18 months (M6-M24)
QA Engineer / Test Specialist	2	0.8	₹120,000.00	₹2,304,000.00	₹69,120,000.00	12 months (M18-M30)
Technical Writer	2	0.4	₹100,000.00	₹960,000.00	₹28,800,000.00	12 months (M24-M36)
Program Coordinator	1	0.5	₹80,000.00	₹480,000.00	₹14,400,000.00	36 months (part-time)
TOTAL TEAM	20	14.0 avg	-	₹58,000,000.00	₹450,000,000.00	-