## Sheet1
WBS ID	Task Name	Start Week	End Week	Duration (Weeks)	Lead Role	Supporting Roles	Effort (PM)	Dependency
1.1	Project Initiation & Governance	1	4	4	Project Manager	Program Coordinator	2	-
1.2	Requirement Elicitation & Clarification	5	10	6	Systems Engineer	PM DRDO Liaison	4	1.1
1.3	System Requirements Document (SRD)	11	18	8	Systems Engineer	PM QA Lead	5	1.2
1.4	Technology Survey & Critical Tech ID	6	17	12	Lead ML/AI Scientist	Lead Thermo Eng Academics	8	1.1
1.5	High-Level DT Framework & Architecture	15	22	8	Software Architect	Systems Eng Lead Roles	6	1.4
1.6	PDD Finalization & PDR Approval	19	26	8	Project Manager	Systems Eng All Leads	4	1.3 1.5
2.1	Feasibility & Modeling Strategy	27	32	6	Lead Thermo Eng	Lead ML Sci Systems Eng	8	1.6
2.2	Detailed Design of 17 DT Blocks	33	48	16	Lead Thermo Eng	Lead ML Sci Data Eng	20	2.1
2.3	Data Strategy & Pre-processing Design	27	38	12	Data Engineer	Lead ML Sci QA Lead	10	1.6
2.4	Integrated System Design (17 DT Blocks)	39	48	10	Software Architect	Systems Eng Lead Thermo	12	2.2
2.5	Hardware & Platform Definition	35	42	8	Systems Engineer	Software Arch QA Lead	6	2.1
2.6	SDD/DDD Finalization & Design Review	45	52	8	Systems Engineer	PM All Technical Leads	6	2.2 2.4 2.5
3.1	Prototype Implementation of DT Blocks	53	66	14	Lead Thermo Eng	Lead ML Sci Soft Arch JE	24	2.6
3.2	Data Handling Training & Validation	53	68	16	Data Engineer	Lead ML Sci Lead Thermo	18	2.3
3.3	Integrated DT Prototype Assembly	63	72	10	Software Architect	Lead Thermo Eng Soft Eng	14	3.1
3.4	Performance Regime Clustering & Tuning	65	72	8	Lead ML/AI Scientist	Data Engineer Lead Thermo	10	3.2
3.5	Prototype Testing & Validation	67	76	10	QA Lead	Lead Thermo Eng QA Team	12	3.3 3.4
3.6	QA & Process Documentation	70	75	6	QA Lead	PM Technical Writers	8	3.5
3.7	CDD & Critical Design Review (CDR)	73	78	6	Systems Engineer	PM All Leads	6	3.6
4.1	Hardware Procurement & Setup	79	90	12	Systems Engineer	Soft Arch Admin Vendors	8	3.7
4.2	Production Software Hardening	85	100	16	Software Architect	GUI Dev Soft Eng QA	18	3.7
4.3	Hardware & Software Integration	99	110	12	Software Architect	Systems Eng Soft Team	14	4.1 4.2
4.4	ATP Procedure & Execution	109	124	16	QA Lead	PM All Teams DRDO	16	4.3
4.5	On-Site Model Training & Validation	95	114	20	Lead ML/AI Scientist	Data Eng Lead Thermo JE	22	4.2
4.6	Acceptance Reports & Final Sign-off	125	130	6	QA Lead	PM Systems Eng	4	4.4 4.5
5.1	Final Documentation Set	131	142	12	Project Manager	Tech Writers All Leads	8	4.6
5.2	Production & Delivery of Final Units	131	140	10	Software Architect	Systems Eng QA Admin	10	4.6
5.3	Transfer of Technology (ToT)	141	150	10	Lead Thermo Eng	Lead ML Sci All Leads	12	5.1
5.4	IPR Sharing & Legal Closure	145	150	6	Project Manager	Legal Advisor	3	5.1
5.5	Project Success & Completion Reports	150	156	7	Project Manager	Systems Eng QA Lead	5	5.3 5.4